## Weekly Summary
Week's end date | Name | Role | Weekly Summary | Main Tasks/Duties Accomplished | Next Targets/ Goals to work on | Completed Training Codes | Issues/Concerns

## Manager Input
Week's End Date | Project Status | Team Involved

## READ ME
Please follow the instructions below to ensure the Power BI report reads your data correctly:
Weekly Summary Column - Enter summaries in third-person point of view. - Example: "Madeline assisted the team with onboarding tasks."
Issues/Concerns Column - If reporting multiple issues, end each one with a period and press Alt + Enter to move to a new line. - Example: - "Software license expired." - "Need more time for QA validation."
Manager Input Sheet - The person preparing the weekly report must go to the "Manager Input" sheet and select: - The correct Week’s End Date - The Overall Program Status for that week: G (Green), Y (Yellow), or R (Red)
Completed Training Codes Column - List multiple training codes by separating each with a comma. - Example: - SAFE-3002WBT, TECH-0091WBT, ISEC-9023WBT

## Dummy Data
Week's end date | Name | Role | Weekly Summary | Main Tasks/Duties Accomplished | Next Targets/ Goals to work on | Completed Training Codes | Issues/Concerns | Week's End Date | Project Status
2025-03-07 | Ben Miles | Project Management | It looks like everyone is required to complete 2 upcoming trainings; Ben completed of them last week. SHUG flights and the control schedule is slowed due to weather this coming week. Flight plans are being revised to reflect a concern by the Aviation Pilots. They have identified that 130 KTS would be more safe in the higher elevation flights, making LiDAR collection less effort for the pilot to maintain consistent airspeed in thin air. Software requests are moving forward. | Training completed: Enterprise Information And Records Management CORP-9049WBT Ongoing SHUG flight plan evaluation and submission. Follow up on Software approvals. Large Load capacity follow-ups. Might see movement on this in the next week. Ongoing project support. Tracking/salesforce/ProjectWise updates. | Completed 2025 Security & Privacy Awareness training Preparing for meeting with CEL interns (Business Analytics group) Scheduled 1:1 with Rebecca Gathering documentation for CEL intern meeting Continuing SHUG flight plan submissions Updated software tracking with recent activity Working on AWS EC2 solutions Creating software update flowchart Drafting script: PG&E Training Module – “Who will collect my data?” Planning outward-facing timeline for project requests (PMO + Intake Form) Discussing project report process with Michael to reduce data availability delays | CORP-9049WBT, CORP-9081WBT, SAFE-2201WBT, TECH-0092WBT | Behind schedule due to weather delays. Client feedback received late, impacting delivery. Need more time to validate QA data. Awaiting training before starting new module. | 2025-03-07 | G
2025-03-07 | Madeline Haroldsen | GIS Specialist | Field days: This week Madeline worked on projects that mainly involved boundary and topographic survey. Office days: For office days, Madline worked on level notes from the Wishon project, put together a field package for and upcoming project, and completed some online trainings. | Assisted in finding section corners in the field Assisted in taking GPS points for a topo survey Gathered maps and documents for a field package | Assist with the Lidar scan in Topock next week Get feedback on my field packages and level notes | TECH-9165WBT, CORP-0375WBT, SAFE-1554WBT, ENVR-0075WBT, GIS-2024WBT, CORP-1100WBT | Short-staffed due to unexpected leave. Interns need additional onboarding. Need clarification on project handoff roles. | 2025-03-14 | G
2025-03-07 | Micheal Heesh | GIS/QA/QC | Eric and Micheal presented in-person (3/6) about the Remote Sensing Catalog updates for the LS&ES All-Hands meeting, which was well received. The 2nd 2025 Catalog update continues alongside the Geosciences and Landbase Conflation requests. | Presented to the LS&ES All-Hands conference (3/6) on the RS Catalog and RS Catalog Viewer. Reviewed and migrated D2 2025 data (CASIE23 part 2) to geodatabase. | Create KMZ footprint & deliver 2nd 2025 RS Catalog update Complete Plumas County ortho request (LandBase Conflation) Request to join RS PMO workshop (RS Viewer updates) Talk to Brandon about adding SSD to PG&E laptop Granted edit access to LS&ES SharePoint “GIS & Mapping Resources” Met with Ryan Gunst (RSPMO) re: QA/QC workload Requested AKM to add Adjusted Survey Control layer Holding on Pending layer projects for Kassim Clarifying OH Basemap needs with Ben | TECH-9162WBT, CORP-9120WBT, QAQC-1001WBT, TECH-0085WBT | Limited access to server during peak hours. Need additional storage space for imagery files. Printer/scanner in field office not working. | 2025-03-21 | Y
2025-03-07 | Yoko Jessica Rader | GIS Specialist | Yoko spent most of the week processing three Orthophoto projects, which went smoothly. She’s waiting on two Tiling Schemas from Paul and Ernie to complete them. She also began record management and security trainings, noting a new AI section—Gen AI is now available through SharePoint. While she has used ChatGPT before, she’s curious how Gen AI compares. Additionally, she’s self-learning how to write project reports, starting with Charca, using training samples, and aims to finish her first draft early next week. | Information & Record Management 2025 2025 Security & Privacy Awareness | Complete Charca Report | CORP-9025WBT, TECH-0110WBT, GIS-2040WBT, CORP-9370WBT, CORP-9912WBT | Unexpected budget cap alert prevented submission. Delay in receiving timesheet summaries from contractors. Multiple team members absent from alignment meeting. | 2025-03-28 | R
2025-03-07 | John Gabriele | GIS Specialist | This week John have been focused on finishing onboarding with PG&E. Lastly, John has accomplished the last PG&E training modules and creating flowcharts of software for data processing. | Finished Onboarding, finished PGE&’s Training Modules Software licensing, downloads and familiarization Attended DOR meetings, introduction to more PG&E land surveyors | Stress test software, start processing data | SAFE-1500WBT, SAFE-1554WBT, SAFE-3002WBT, TECH-0001WBT, TECH-9164WBT, SAFE-0300, PSOS-2500WBT, CORP-0375WBT, CORP-9049WBT, EQIP-0200WBT, ISEC-9025WBT, TECH-0081 | Waiting on manager approval to schedule field shadowing. VPN access blocked during fieldwork attempt.
2025-03-14 | Ben Miles | Project Management | First SHUG flights are going to happen early next week, the first 2 flight plans are submitted. The PM on the SHUG side and Ben have been working to set the priority and timeline for all ongoing collections. There will likely be at least one or two flight plans that we will need to adjusted | SHUG flight plan evaluation and submission. Large Load capacity follow ups. Actively pursuing AWS Ec2 working solutions Ongoing project support. Tracking/salesforce/ProjectWise updates. Follow up on Software approvals. | Ben-Ongoing SHUG flight plan submissions Ben-Update software tracking and make sure all recent activity is up to date. Ben-Review Pole Conflation (933 poles) Ben-Educational material: Ben-Publish outward facing timeline for project requests. This should fall on the PMO, in conjunction with the Intake form. Ben-Create project report process to help mitigate time between process completion and data being made available to the catalog. | LAND-9300WBT, LAND-9301WBT, SAFE-0615WBT, SAFE-0511WBT, SAFE-1491WBT, SAFE-1554WBT, SAFE-1500WBT, SAFE-0120WBT, TECH-0001WBT, TECH-9164WBT, TECH-9165WBT. TECH-9162WBT, ENVR-9028WBT, ENVR-0070WBT, ISEC-9021WBT, TECH-0081WBT, CORP-9192WBT | Stakeholder feedback loop delayed final decision. Experienced lag while using cloud-based approval forms. Risk tracker dashboard not syncing with updated milestones.
2025-03-14 | Madeline Haroldsen | GIS Specialist | Madi split her time between fieldwork and office work. In the field, she worked on several projects mostly consisting of boundary and topographic surveys and assisted with her first terrestrial lidar scan. In the office Madi completed additional trainings and worked on level (settlement survey) notes and land distribution inquiries. | Trainings/onboarding Supported the land survey team with several ongoing projects | Madi-Memorize the most frequently used point codes Madi-Continue to familiarize with the terminology, technology and techniques used in land survey | GIS-3055WBT, FIELD-1120WBT, CORP-9500WBT, SAFE-1122WBT, TECH-2090WBT, GIS-DATAMAN-2024, ENVR-2210WBT, QAQC-ADVANCED-315WBT | Data collector battery died mid-survey session. Field map layers not aligning with GPS signals.
2025-03-14 | Micheal Heesh | GIS/QA/QC | Michael completed the SARA24 (Shasta County ED Collection) QA/QC, with a report is ready for delivery to the PMO. The Conflation Landbase team requested an ortho pull for Siskiyou and Plumas County (~12000 files) which is in progress. | Finished with SARA24 QA/QC pilot and send report to the RS PMO team. Stared with ortho data request for Siskiyou and Plumas County to aid in the Conflation Landbase project. | Michael-Continue with 2nd delivery of RS Catalog. Michael-Start gathering projects for the Pending layer for Kassim. Michael-Speak with Eric on interface updates on the catalog. Michael-Update documentation and training for RS Catalog Front-End viewer. Michael-Await NV5 ET Eng 23/24 deliveries. Michael-Request AKM to add new layer for Adjusted Survey Control like the Remote Sensing Catalog. Michael-Clarify with Ben on OH Basemap requests and future needs | LAND-9300WBT, LAND-9301WBT. SAFE-0615WBT, SAFE-0511WBT, SAFE-1491WBT, SAFE-1554WBT, SAFE-1500WBT, SAFE-0120WBT, TECH-0001WBT, TECH-9164WBT, TECH-9165WBT, TECH-9162WBT, ENVR-9028WBT, ENVR-0070WBT, CORP-9192WBT, CORP-9124WBT | Server-side QA tool version is outdated. Control point data from last flight has anomalies. Noise in LiDAR dataset affected validation script.
2025-03-14 | Yoko Jessica Rader | GIS Specialist | Yoko has many orthophotos to process now that TIMP is complete. She worked on the Santa Rosa project, which was flown with four flights. She also worked on troubleshooting the orthophoto for A291 Charca. She completed the A271 Eastshore Clawiters Orthophoto. | Orthophoto Processing: A271 Eastshore Clawiter Orthophoto Shasta QA/QC Santa Rosa UAS Orthophoto Troubleshooting | Yoko-A292 Topock Phase 2B Survey - Start Orthophoto Processing Yoko-112 Oakland D1116 - Start Orthophoto Processing Yoko-A291 Charca - Continue Troubleshooting | LAND-9300WBT, LAND-9301WBT, SAFE-0615WBT, SAFE-0511WBT, SAFE-1491WBT, SAFE-1554WBT, SAFE-1500WBT, SAFE-0120WBT, SAFE-3002WBT, TECH-0001WBT, TECH-9164WBT, TECH-9165WBT, ENVR-9028WBT, ENVR-0070WBT, CORP-9192WBT, CORP-9124WBT, ISEC-9023WBT, ISEC-9023 | GIS software crashed multiple times during batch export. SharePoint permissions inconsistent across folders. Field staff submitted shapefiles without metadata.
2025-03-21 | Ben Miles | Project Management | Ben coordinated with Evergreen team on SHUG project deliverables and ompleted QA review and followed up with PG&E stakeholders on status updates. | Finalized boundary shapefile Met with Evergreen team for alignment Integrated parcel overlays Updated FGDC metadata | Assist with elevation verification Schedule client review Create layer documentation Finalize QA report | CORP-0301WBT, QA-1100WBT, SAFE-2345WBT | Client feedback pending. Software crash.
2025-03-21 | Madeline Haroldsen | GIS Specialist | Madeline worked on orthophoto processing for San Mateo and validated shapefiles and began compiling QA documentation for submission. | Completed QA review for SHUG section C Processed orthophoto files Validated spatial accuracy Reviewed Santa Clara QA logs | Prep for Topock QA Verify discrepancies Review Charca QA | GIS-0201WBT, SAFE-8840WBT, GIS-0201WBT, CORP-9912WBT | Delayed access to drawing tool due to pending license. Conflicting instructions from client regarding deliverables. Ambiguity in boundary lines for new project request.
2025-03-21 | Micheal Heesh | GIS/QA/QC | Micheal reviewed QA logs from Santa Clara and began preparing the report for upcoming review. He also cross-checked spatial references and fixed naming inconsistencies. | Logged GPS coordinates in field Reviewed Santa Clara QA logs QA’d San Mateo overlays Fixed layer naming inconsistencies | Finalize QA report Coordinate with GIS team Review Charca QA Assist with field QA | QA-1100WBT, CORP-1105WBT | Trouble accessing archived QA references from 2023. Confusion over versioning of orthophoto files in SharePoint.
2025-03-21 | Yoko Jessica Rader | GIS Specialist | Yoko oversaw GIS data integration from multiple SHUG field visits. She reviewed parcel overlays and approved new update schema. | Integrated SHUG parcel overlays Reviewed updated symbology Approved schema for new dataset Conducted intern QA training | Meet with QA/QC team for final edits Coordinate onboarding with interns Create documentation for Evergreen Assist with elevation verification | GIS-LEAD201WBT, SAFE-0325WBT, GIS-LEAD201WBT, SAFE-8840WBT, CORP-0301WBT | Coordination with QA/QC team still not finalized. Delano ortho had duplicate tiles causing confusion. Formatting error in uploaded KMZ files. Training materials for new interns are outdated.
2025-03-21 | John Gabriele | GIS Specialist | John conducted ground-truthing at SHUG site, logged GPS points, and submitted updates to survey map. John also noted discrepancies with original parcel IDs. | Submitted survey corrections Captured imagery of flagged parcels Updated status tracker for PG&E Logged GPS coordinates at SHUG checkpoints | Recheck Site 3 coordinates Verify discrepancies with GIS office | FIELD-2210WBT, CORP-0301WBT | GPS unit malfunction. Missing field notes.
2025-03-28 | Ben Miles | Project Management | Ben worked on streamlining client communication protocols and finalized the data submission process for SHUG Phase 3. Ben coordinated with GIS and QA teams to ensure alignment across deliverables. Ben helped draft the training rollout timeline. Ben Also began reviewing budget projections for Q3. | Finalized SHUG Phase 3 submission documents Led sync meeting with GIS and QA teams Created outline for Q3 budget forecasting Initiated risk management documentation | Meet with finance team to finalize projections Start the workflow automation outline Continue internal review of project milestones Prepare training handouts | SAFE-3022WBT, TECH-9004WBT, CORP-1111WBT | Client requested a change in scope mid-week. Budget tool integration with SharePoint failed.
2025-03-28 | Madeline Haroldsen | GIS Specialist | Madeline field visit completed for A310 boundary survey. Madeline marked two data discrepancies and shared findings. Madeline started compiling DOR reports and refining drawing layers. | A310 Boundary Field Survey Initial DOR Report Draft Drawing layer cleanup for Santa Clara | Complete DOR report Re-check legacy survey files | CORP-1100WBT, TECH-0022WBT, GIS-2023WBT, SAFE-1500WBT | Bluetooth connection dropped during GNSS tracking. Unexpected rain caused two-day delay in fieldwork. Missed training recap due to conflicting meeting invite.
2025-03-28 | Micheal Heesh | GIS/QA/QC | Micheal completed QA/QC pass on 5 orthophotos. Micheal began coordinating corrections on misaligned ground control points. Micheal trained a new junior QA analyst. | Reviewed and approved 5 orthophotos Logged errors in flight line alignment Conducted peer QA training Provided QC feedback to GIS team | Start QC process for Santa Clara batch Re-run control point adjustment for A281 Prepare QA feedback doc for team | TECH-9041WBT, GIS-2025WBT | Field data upload inconsistencies.
2025-03-28 | Yoko Jessica Rader | GIS Specialist | Yoko processed several new orthophotos, including Topock and Delano. Yoko collaborated with Micheal on improving ground control data accuracy. Yoko spent time onboarding interns. | A281 Topock Orthophoto Processing Delano Batch Review Intern orientation walkthrough | Finalize Delano outputs Upload results to SharePoint Review new field request from Ben | SAFE-1002WBT | System crashed during orthophoto export. Need faster access to SharePoint folders. Intern unsure about training path.
2025-03-28 | John Gabriele | GIS Specialist | John continued onboarding trainings and shadowed Ben during team meetings. John practiced using ProjectWise and updated internal documentation templates. | Completed SAFE orientation modules Shadowed Ben during training rollout discussion Updated documentation template for project kickoff | Join GIS QA team meeting Submit first map draft | SAFE-1011WBT, CORP-0100WBT | Still adjusting to ProjectWise system. Issues logging into the survey tablet remotely. Orientation materials missing links to onboarding portal. Minor GPS drift noticed in recorded points. Still not granted access to folder templates.